## Slide 1
Monthly Update – April 2024

## Slide 2
April Delivery
Presented & Submitted market research report to the team
Assessed ERP for data quality; prepared rough draft of data quality assessment report
Received and currently reviewing financial, sales, production, and inventory data, Created KPIs and ratios; pending internal review
Brainstormed semi-automated data capture system with stakeholders
Developed the mockup of profitability dashboards for 2 business lines
Tested Airtable for RTS data capture model, evaluating pros and cons as a revenue management tool for enhanced visibility.
Developed an RTS Base in Airtable with proficient version control and tested automated email functionalities; also established a formulaic base, including syntax, descriptions, and troubleshooting for LFT Team.
Presented Airtable's suitability for our needs to stakeholders and showcased its compatibility with Power BI via REST API integration.
Demonstrated seamless EOS data capture using native Airtable Forms.

## Slide 3
Way Forward – May Plan
Produce Data Quality Assessment Report
Establish enterprise-wide data governance through collaboration with all data owners
Provide Profitability and Working Capital Dashboards
Develop the mockup of Daily Production Report and Cost Centers Dashboards
Formulate KPIs and OKRs based on dashboard insights to enhance deliverables and foster growth
Design and deploy Project R&D and Project costing Dashboard
Implement the data federation policies and construct data pipelines from the ERP
Design and deploy the Financial Analysis Deepdive Dashboard and test it’s functionality
Construct scheduled workflows for automation of data refreshes and reporting

## Slide 4
Thank You Flipcarbon Integrated Solutions Pvt. Ltd Info@flipcarbon.com www.flipcarbon.com
Bangalore | Chennai | Delhi | Mumbai | Ranchi | International