## 90 Days Plan (hidden)
Business Consulting Agenda
Focus Area | Sl No | Task | October | November | December | January
HR & Finance Baseline assessment | 1 | Onboarding the client
| 2 | Review and analyse existing Financials for growth tends and key financial ratios
| 3 | Conduct the HR Baseline Assessment along with the HR Spoc and highlight the gap areas if any
| 4 | Conduct the Finance baseline assessment along with Finance team and highlight gap areas if any
| 5 | Review and analyse existing Financials for growth tends and key financial ratios
Business Strategy & Organizational Goals | 1 | Strategy Session with Founders and key management team
| 1.1 | Discuss, brainstorm and finalize the winning aspiration for the strategy period
| 1.2 | Discuss, brainstorm and finalize the Go to market strategy i.e
| 1.2.1 | Where to play - Geography, Industry, Customer, channels etc
| 1.2.2 | How to win in the defined markets
| 1.3 | Discuss and define the capabilities required for winning - resources, funds, tools, technology etc
| 1.4 | Brainstorm on the product strategy and international expansion
| 2 | Define business critical goals to achieve the winning aspirations
| 3 | Scripting Organisational Goals for 2023-24
Org Structure Alignment | 1 | Assess Organizational Goals and Needs, Review of "As Is" Org. Structure
| 2 | Propose the Right structure: - Conduct the "Fit Tests" and "Good Design Tests" to ascertain the right structure.
| 3 | Define Reporting Relationships: - Determine the hierarchy of authority and reporting lines.
| 4 | Identify the Unique roles
Role Clarity | 1 | Gather Job Information for Leadership Roles
| 2 | Outline Key Elements
| 3 | Set KRAs for all the existing roles
| 4 | Specify Qualifications and Requirements
| 5 | Review and Approval
Strategic Financial Plan | 1 | Discuss and align on yearly targets for key financial deliverables i.e.
| 1.1 | revenue for different markets, industry, customer, channels
| 1.2 | Gross margins for different markets, industry, customer and channels
| 1.3 | Direct costs in terms of people, tools, technology based on Org structure defined
| 1.4 | Salary for different skill sets, increments etc
| 1.5 | Other Fixed Costs and optimization targets for controllable fixed costs
| 1.6 | Sales and marketing costs in different markets and in line with the growth in topline
| 1.7 | Understand the aspirations for International expansions and estimate costs associated with it
| 1.8 | Evaluate and estimate the capex requirements
| 1.9 | Evaluate, estimate and optimize DSO, DPO and other working capital assumptions
| 2 | Evaluate funding requirements and define the appropriate capital structure - debt and equity
| 3 | Benchmark with the compettion on key financial numbers and ratio
| 4 | Finalize all key assumptions and create the financials - PL, BS and Cashflow
| 5 | Compute Unit Economics
| 6 | Analysing the key metircs i.e. burn rate and runway available
| 7 | Deliver the final financial plan
Talent Acquisition | 1 | Review & understand the current TA & Recruitment Process
| 2 | Preparation of JD for all open positions
| 3 | Evaluate the existing recruitment agencies and Onboard new ones if required
| 4 | Assisting the Current HR
Cash flow forecasting & Management | 1 | Redraft current policies as per govt. madate
| 2 | Get Approval from Management & Document the same
| 3 | Communicate the altered policies to all the employees
PMS Framework | 4
| 4.1 | Assess the current PMS system
| 4.2 | Define Performance Objectives: - Establish clear and measurable performance objectives aligned with organizational goals. - Define KRAs and KPIs to assess employee performance.
| 4.3 | Develop Performance Evaluation Processes: - Design processes for regular performance evaluations. - Determine the methods and tools for assessing employee performance.
| 4.4 | Establishing Performance Expectations - Feedback & Coaching - Implement mechanisms for ongoing feedback and coaching - Encourage open communication to address performance issues, provide recognition, and set development goals.
| 4.5 | Set Development Plans and Rewards: - Collaborate on individual development plans.

## 120 Days Plan
Business Consulting Agenda
Focus Area | Sl No | Task | December | January | February | March
Strategy Articulation and Integration | 1 | Discuss, brainstorm and finalize the winning aspiration for the strategy period
| 2 | Discuss, brainstorm and finalize the Go to market strategy i.e
| 3 | Where to play - Geography, Industry, Customer, channels etc
| 4 | How to win in the defined markets
| 5 | Discuss and define the capabilities required for winning - resources, funds, tools, technology etc
Product Business Model - Evaluation and Business Plan | 1 | Brainstorm on the strategy for all 3 products
| 2 | Formulate the business plans for ENECON,ENELYX,ALTEC
| 3 | Create a strategic financial plan for ENECON, ENELEX and ALTEC
| 4 | Sensitivity analysis, ROI, Payback period - evaluation and recommendation
Aligning Organization Structure and Role Expectations | 1 | Assess Organizational Goals and Needs, Review of "As Is" Org. Structure
| 2 | Propose the business appropriate structure: - Conduct the "Fit Tests" and "Good Design Tests" to ascertain the right structure.
| 3 | Define Reporting Relationships: - Determine the hierarchy of authority and reporting lines.
| 4 | Identify the Unique roles
Strategic Financial Plan | 1 | Discuss and align on yearly targets for key financial deliverables i.e.
| 2 | Revenue and Gross margins targets for different markets, industry, customer, channels
| 3 | Direct costs and other fixed costs in terms of people, tools, technology, marketing, sales based on Org structure defined
| 4 | Evaluate and estimate the capex requirements
| 5 | Evaluate, estimate and optimize DSO, DPO and other working capital assumptions
| 6 | Evaluate funding requirements and define the appropriate capital structure - debt and equity
| 7 | Deliver the final financial plan
Annual Operating Plan | 1 | AOP launch, setting expectations, discussing key people involvement and finalizing the plan and calendar
| 2 | Sharing the formats, data requirement with different functions for data
| 4 | Receipt of details from Client's Team
| 5 | Preparation of AOP
Articulation of Business Critical Goals / KPIs | 1 | Identify business critical goals for each financial year in 4 categories : - financial goals, customer goals, business process goals and people development/ capability goals based on the strategy
| 2 | Identify the critical KPIs to be delivered against each of these goals
| 3 | Identify timelines for delivery of each of these goals
| 4 | Align the senior management and founders
| 5 | Make changes based on the discussion with the founders and senior management and start the implementation process
Quarterly Business Review | 1 | Define functional reviews and calendarize them
| 2 | Define the MIS And dashboards to be reviewed by each functions
| 3 | Create actionables and responsibilities out of review
| 4 | Evaluate next quarter's target and make changes if required
| 5 | Communicate the targets to the relevant functions
| 6 | Analyse and communicate the quarterly targets with all functions
Performance management | 1 | Designing Performance Management Framework (Including approach for current year appraisal)
| 2 | Goals Scripted for Leadership Team (Both What & How aspect of deliverables)
Monthly Performance Review | 1 | Performance of all functions for the month and YTD